## Sheet
Projet A3XX
. | Internal number | Line identifier | Type of activity | Name | Description | Duration | Planned start | Planned finish | Actual start | Actual Finish | Predecessor | Successor | Current baseline date | Global baseline date
| 14029533533 | 1 | Consolidated task | Category_1 |  | 4992d | 2007-01-01 | 2020-09-01 | 2014-10-01 |  |  |  | 2020-09-01
| 14054855433 | 2 | Consolidated task | Activitie_1.1 |  | 0d | 2007-01-01 | 2007-01-01
| 14056172733 | 3 | Consolidated task | Activitie_1.2 |  | 0d | 2007-01-01 | 2007-01-01
| 14059508933 | 4 | Consolidated task | Activitie_1.3 |  | 0d | 2007-01-01 | 2007-01-01
| 14055582133 | 5 | Consolidated task | Category_2 |  | 154d | 2015-01-20 | 2015-08-24 | 2015-01-20 | 2015-08-24 |  |  | 2015-08-24
| 14057326833 | 6 | Consolidated task | Category_3 |  | 154d | 2015-01-20 | 2015-08-24 | 2015-01-20 | 2015-08-24 |  |  | 2015-08-24
| 14058913033 | 7 | ACT_PLAN | Activitie_3.1 |  | 0d | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 |  | 8FS;9FS
| 14054774833 | 8 | ACT_PLAN | Activitie_3.2 |  | 0d | 2015-02-13 | 2015-02-13 | 2015-02-13 | 2015-02-13 | 7FS
| 14059309133 | 9 | ACT_PLAN | Activitie_3.3 |  | 23d | 2015-01-20 | 2015-02-20 | 2015-01-20 | 2015-02-20 | 7FS | 10FS
| 14056165633 | 10 | ACT_PLAN | Activitie_3.4 |  | 0d | 2015-02-20 | 2015-02-20 | 2015-02-20 | 2015-02-20 | 9FS | 11FS;12FS
| 14056890333 | 11 | ACT_PLAN | Activitie_3.5 |  | 0d | 2015-03-04 | 2015-03-04 | 2015-03-04 | 2015-03-04 | 10FS | 13FS
| 14053997633 | 12 | ACT_PLAN | Activitie_3.6 |  | 0d | 2015-05-07 | 2015-05-07 | 2015-05-07 | 2015-05-07 | 10FS | 15FS
| 14058218733 | 13 | ACT_PLAN | Activitie_3.7 |  | 46d | 2015-03-06 | 2015-05-10 | 2015-03-06 | 2015-05-10 | 11FS | 15FS
| 14055676833 | 14 | ACT_PLAN | Activitie_3.8 |  | 0d | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | 15FS | 16FS
| 14059714533 | 15 | ACT_PLAN | Activitie_3.9 |  | 19d | 2015-06-22 | 2015-07-17 | 2015-06-22 | 2015-07-17 | 12FS;13FS;14FS | 14FS
| 14056442533 | 16 | ACT_PLAN | Activitie_3.10 |  | 0d | 2015-08-19 | 2015-08-19 | 2015-08-19 | 2015-08-19 | 14FS | 17FS
| 14057437933 | 17 | ACT_PLAN | Activitie_3.11 |  | 0d | 2015-08-24 | 2015-08-24 | 2015-08-24 | 2015-08-24 | 16FS